## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: |  | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | STAFFING | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
System Request | 1 | 1 | 0 | 0 | 25% | Lamia, Ananya
Feasibility Analysis | 2 | 2 | 0 | 0 | 100% | Tasneem
Workplan | 4 | 2 | 0 | 0 | 35% | Muhtadi, Zarin
Staffing | 4 | 1 | 0 | 0 | 10% | Lamia
Research | 5 | 1 |  |  |  | Ananya
Strategizing | 6 | 1 | 0 | 0 | 85% | Zarin
Requirement Gathering | 7 | 2 | 0 | 0 | 85% | Muhtadi, Tasneem
Requirement Analysis | 9 | 1 | 0 | 0 | 50% | Lamia
Process & Data Model | 10 | 2 | 0 | 0 | 60% | Ananya
Software Design | 12 | 3 | 0 | 0 | 75% | Lamia, Muhtadi
Network Design | 14 | 1 | 0 | 0 | 100% | Tasneem, Zarin
Programme Interface | 15 | 3 | 0 | 0 | 60% | Ananya, Muhtadi
Database Design | 18 | 1 | 0 | 0 | 0% | Tasneem, Lamia
User Interface Design | 18 | 3 | 0 | 0 | 50% | Zarin, Lamia
Back-end Coding | 21 | 4 | 0 | 0 | 0% | Lamia, Muhtadi, Ananya
Front-end Coding | 25 | 3 | 0 | 0 | 1% | Tasneem, Ananya, Lamia
Program Development | 28 | 3 | 0 | 0 | 80% | Lamia, Ananya, Muhtadi
Testing | 31 | 2 | 0 | 0 | 0% | Zarin, Ananya
Training | 33 | 3 | 0 | 0 | 0% | Zarin, Tasneem